## Oct week 1
Week | Task | Priority | Details
05/10 - 09/10
Deployment | Video Over RTSP protocol |  | Done
| Storage for simulated video |  | Done
| Update in Github Actions flow | Recurring | Done
| Check for Storage for all containers | Less
| Deployment hardware location | Less
Storage integration with Smart city
| Git Integration and cluster config |  | Done
GKE | Provision test cluster with IAM config |  | Done
| Connection with Anthos |  | Done
Anthos | Theoreticals | Recurring | Progressing
| IAM configuration | Recurring | Done for Anthos
| New cluster |  | Done
| Connection between Cluster |  | Done
| Azure Anthos |  | Integration issues for service mesh
| GKE setup and config |  | Done
| GKE Anthos |  | Done
| GKE IAM & Service Mesh |  | Done
| Service Mesh Config |  | Done
| Service Mesh Setup |  | Done

## Oct week 2
Week | Task | Priority | Details
12/10-16/10
GKE | GKE Deployment Analysis | Done | Issue with certificate
| GKE Deployment Tests | Done
| GKE Deployment Smartcity integration | Done
| GKE IAM management | Done
| GKE API management | Done
Anthos | Config Health Management | Done
| Service Security Management | Done
| Anthos Sample Deployment on Google Cloud | Done
Deployment | New cluster Deployment Divya | Done | Done
| Update in Github Actions flow | Recurring
| Check for Storage for all containers | Less
| Deployment hardware location | Less
| Storage integration with Smart city | Done
| Git Integration and cluster config | Done

## Oct week 3
Week | Task | Priority | Details
12/10-16/10
GKE | Rewrite kubernetes Deployment Scripts | Done
| Rectify Certicatie issue | High
| Cascade Lake Servers | Done | GCP servers is able to configure
Application Deployment Strategy
Anthos | Infrastructure Deployment Strategy
API Deployment
Deployment | Update in Github Actions flow | Recurring
Connection with Anthos and github repo